## Sheet1
PLAN DEVIATION SUMMARY
[PROJECT NAME]
[CONTRACT NO]
Issue # | Date | Deviation | Summary | Error Cost | Cumulative Error Cost | Contract Time Delay | Change Order Code
1 |  |  |  |  | 0
2 |  |  |  |  | 0
3 |  |  |  |  | 0
4 |  |  |  |  | 0
5 |  |  |  |  | 0
6 |  |  |  |  | 0
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0
Change Order Codes
# | Type | Summary
1 | Balance CO | Code used for final change order to balance proposed contract quantities with actual used quantities
2 | Design | Code used for change orders caused by design error. These design errors can be made by Consultant or City. Reason code encompasses many things, from errors in plans, utility conflicts that could have been prevented, start dates and contract times that go past seeding date/late into winter where cold weather protection is required, inadequate underground exploration, etc.
3 | Unforeseen Field Conditions | Code used for change orders caused by unforeseen field conditions. This includes things such as unforeseen subsurface conditions, weather, etc. Examples for unforeseen subsurface conditions include boulders, telephone poles, pockets of materials that aren't consistent with the rest of the site, etc. Does not include unforeseen subsurface items that could have been caught easily with soil borings (large portion of underground material is junk and needs to be stabilized, etc.). Examples for weather include above average percipitation, uncommon cold weather, etc. Does not include weather related items due to design error (contract dates with ending past seeding window or paving in cold weather).
4 | Private Utility Company Delays | Code used for change orders caused by private utility company delays. Examples include private utility companies claiming to be out of the way in design when they are not, private utility companies not relocating in time frame given, private utilities relocating but still in the way, private utilities not locating abandoned lines, etc. Does not include unforeseen utility conflicts that could have been easily avoided in design process (inadequate time given to relocate, not contacting utility to determine position, etc.)
5 | Contractor Initiated | Code used for change orders caused by Contractor. Examples include substituting materials, value engineering, etc.
6 | Owner Initiated | Code used for change orders initiated by Owner. Examples include adding additional work at City's request, design standard changes during project, scope changes, etc.